## TemplateDoHistorico - Model Nam
Claude Sonnet 4.6
Phase | Code | Title | Descriptioin | Status | Agent use | Prompt(s) | Prompt Type | Issues | Overall result | Overall sentiment | Observations
Initial Config | P101 | Install Node.js and npm | Install Node.js (LTS) and npm on your local machine. Verify with `node -v` and `npm -v`. | Done | not |  | None |  | Unused
Initial Config | P102 | Install Git | Install Git and configure global user name and email. | Done | not |  | None |  | Unused
Initial Config | P103 | Create GitHub repositories | Create two GitHub repositories under a parent `sistema/` folder: `sistema-frontend` and `sistema-backend`, as required by the final repo spec. | Done | not |  | None |  | Unused |  | add remains docs
Initial Config | P104 | Initialize frontend project | Scaffold a React + TypeScript project using Vite (`npm create vite@latest`). Select the React + TypeScript template. | Done | not |  | None |  | Unused
Initial Config | P105 | Install and configure Tailwind CSS | Install Tailwind CSS and its dependencies. Configure `tailwind.config.js` and add Tailwind directives to the global CSS file. | Done | not |  | None |  | Unused
Initial Config | P106 | Initialize backend project | Create a Node.js + TypeScript project for the backend. Run `npm init`, install TypeScript, and configure `tsconfig.json`. | Done | not |  | None |  | Unused
Initial Config | P107 | Install Express and types | Install Express and `@types/express` in the backend project. | Done | not |  | None |  | Unused
Initial Config | P108 | Configure ESLint and Prettier | Install and configure ESLint and Prettier for both frontend and backend to enforce consistent code style. | Done | not |  | None |  | Unused
Initial Config | P109 | Set up .gitignore files | Create proper `.gitignore` files for both projects (ignoring `node_modules`, `.env`, `dist`, etc.). | Done | not |  | None |  | Unused
Initial Config | P110 | Create Excel experiment log | Create `HistóricoDoMeuExperimento.xlsx` in the repository root to log the experiment history as required. | Done | not |  | None |  | Unused
Initial Config | P111 | Create partner review placeholder | Create `RevisãoDoSistemaDoMeuColega.md` in the repository root (to be filled in Phase 8). | Done | not |  | None |  | Unused
Initial Config | P112 | Push initial code to GitHub | Commit and push the initial scaffolding for both frontend and backend to their respective GitHub repositories. | Done | not |  | None |  | Unused
Agent Config | P201 | Install VS Code | Install Visual Studio Code on your local machine if not already installed. | Done | not |  | None |  | Unused
Agent Config | P202 | Install Claude Code extension | Install the Claude Code agent in VS Code following Anthropic's official setup instructions. | Done | not |  | None |  | Unused
Agent Config | P203 | Authenticate Claude Code | Log in and authenticate the Claude Code extension with your Anthropic account. | Done | not |  | None |  | Unused
Agent Config | P204 | Create CLAUDE.md for frontend | Create a `CLAUDE.md` file in the frontend repo with persistent instructions: stack (React, TypeScript, Tailwind), localStorage as the data layer, coding conventions, folder structure, and system domain context. | Done | yes | In the frontend, add a "Hello World" message on the App component | Ask before edit | None | Excelent | Agents and their agents.md files propely Configurated
Agent Config | P205 | Create CLAUDE.md for backend | Create a `CLAUDE.md` file in the backend repo with persistent instructions: Express + TypeScript, stateless architecture (no database), pdfkit for PDF generation, grading and CSV logic only, and API design conventions. | Done | yes | In the backend, add the "Hello World" message before "Serve is running" | Ask before edit | None | Excelent | Agents and their agents.md files propely Configurated
Agent Config | P206 | Define agent skills and tools | Document which Claude Code built-in tools will be used (file editing, terminal, search). Configure or enable them as needed in the project. | Canceled | not |  | None |  | Unused |  | Not necessary
Agent Config | P207 | Validate agent setup | Run a simple test prompt in Claude Code (e.g., "create a Hello World Express route") to confirm the agent is working inside both projects. | Done | yes | create a Hello World Express route | Ask before edit | None | Excelent
Architecture | P301 | Define frontend folder structure | Create the frontend folder structure: `components/`, `pages/`, `hooks/`, `services/`, `types/`, `utils/`, `assets/`. | Done | yes | Create the frontend folder structure as instructed in the file System/Frontend/CLAUDE.md | Plan | None | Ok | Pre-created some files whose use is uncertain
Architecture | P302 | Define backend folder structure | Create the backend folder structure: `controllers/`, `routes/`, `services/`, `utils/`, `types/`, `middlewares/`. | Done | yes | Create the backend folder structure as instructed in the file System/backend/CLAUDE.md | Plan | None | Ok | Pre-created some files whose use is uncertain
Architecture | P303 | Install frontend libraries | Install: React Router (navigation), Axios (HTTP client to call backend), and `papaparse` (CSV parsing on the frontend for student response uploads). | Done | yes | now, we need to Install frontend libraries. install the follow: - React Router (navigation) - Axios (HTTP client to call backend) - `papaparse` (CSV parsing on the frontend for student response uploads). | Ask before edit | None | Excelent | Given that the prompt wasn't very clear, it was necessary to specify that the installation should be done one by one.
Architecture | P304 | Install backend libraries | Install: `cors`, `dotenv`, `pdfkit` + `@types/pdfkit` (PDF generation), `csv-parse` (parsing uploaded CSVs), and `multer` (handling CSV file uploads from the frontend). | Done | yes | now, let's Install backend libraries. install the following: `cors`, `dotenv`, `pdfkit` + `@types/pdfkit` (PDF generation), `csv-parse` (parsing uploaded CSVs), and `multer` (handling CSV file uploads from the frontend). the installation should be done one by one. | Ask before edit | None | Excelent | This prompt was more accurate and provided a better solution.
Architecture | P305 | Define TypeScript types | Create shared TypeScript interfaces: `Question`, `Alternative`, `Exam`, `ExamIdentificationMode` (letter power-of-two), `GeneratedExam`, `AnswerKey`, `StudentResponse`, `GradingResult`, `GradeReport`. | Done | yes | Define TypeScript types. In the frontend, create shared TypeScript interfaces if they don't exist: `Question`, `Alternative`, `Exam`, `ExamIdentificationMode` (letter power-of-two), `GeneratedExam`, `AnswerKey`, `StudentResponse`, `GradingResult`, `GradeReport`. | Ask before edit | None | Excelent | Most types already exist in the previous prompt | After those changes, I confused the word "staged" with "stashed" when I asked to commit the changes, and it made Claude confused with the git files' status, accusing previous changes of not being committed. But according to vscode, only these changes were modified (and staged). Even confused, it suggested the correct bash commit command, but I rejected it to better understand the scenario (even suggesting the correct bash commit command). After asking for the Git file status, Claude said the correct status, according to Vs Code. Better be careful with the words.
Architecture | P306 | Create localStorage service | Build a typed `localStorageService.ts` utility in the frontend that handles all read/write operations for questions and exams, with JSON serialization and error handling. | Canceled | not |  |  |  | Unused |  | Canceled bc it already created during the structure scaffolding
Architecture | P307 | Define Tailwind design tokens | Research design references from similar apps (e.g., Google Forms). Define color palette, typography scale, spacing, and button/input styles as Tailwind theme extensions in `tailwind.config.js`. | Done | yes | Prompt 1: You are now helping define the design system for a web application for creating and grading academic exams. Analyze the visual identity of the images in the DS Ref to get all references. Extract and synthesize a cohesive design system with: 1. Color palette (primary, secondary, neutral, success, warning, error) 2. Typography scale (font family, sizes h1–h6, body, small, weights) 3. Spacing scale (consistent step values) 4. Border radius values 5. Shadow levels 6. Button variants (primary, secondary, ghost, danger) 7. Input and textarea base styles Then output the complete tailwind.config.js theme extension using these tokens, ready to paste into our project. Use CSS variable names prefixed with `--agt-` for any values that need to be referenced in components. ------------------------ Prompt 2: Now create a src/components/DesignPreview.tsx page that renders a visual reference of all tokens: color swatches, type scale, button variants, and input examples. Use only the tokens you just defined. | Ask before edit | None | Excelent | I'll always use.
Architecture | P308 | Create base UI components | Scaffold reusable components: `Button`, `Input`, `Textarea`, `Modal`, `Table`, `Card`, `Badge`, `FormLayout`, and `PageHeader`. | Done | yes | Prompt 1: Let's build the base UI component library for our exam management system. Before creating any component, define the following rules that ALL components must follow: 1. Every component lives in src/components/ in its own file (e.g., Button.tsx, Modal.tsx) 2. Every component exports its Props interface named {ComponentName}Props 3. Every component uses only Tailwind classes — no inline styles 4. Every component uses only the design tokens defined in tailwind.config.js — no hardcoded colors or sizes 5. Every component must have a default export 6. No component may import from another component in this batch (they must be fully independent primitives) Confirm you understood these rules before we proceed. --------------------- Prompt 2 (template to create inidividual components with their own properties): Create the [ComponentName] component following the rules we defined. Props it must support: - [list props] Variants it must support: - [list variants] Do not create any other file. Only src/components/[ComponentName].tsx. | Ask before edit | None | Excelent | Prompt 1: OK Prompt 2: Better improve it with an example in the next time
Architecture | P309 | Configure environment variables | Create `.env` and `.env.example` for both projects. Frontend: `VITE_API_BASE_URL`. Backend: `PORT`. | Done | not |  | None | None | Unused
Architecture | P310 | Define Git flow and commit conventions | Document branching strategy (`main`, `develop`, `feature/P{n}-{code}-{slug}`), commit message format (Conventional Commits), and push rules. Add to README. | Done | not |  | None | None | Unused
Architecture | P311 | Write initial README.md files | Write initial README.md for both repos: project description, stack, how to run locally, folder structure, and environment variable reference. | Done | yes | now, based on the current project state, update the README.md for both repos: project description, stack, how to run locally, folder structure, and environment variable reference, and what you'd consider important. | Ask before edit | None | Excelent
Architecture | P312 | Run projects locally | Start both the frontend dev server and the backend (nodemon + ts-node). Verify the frontend can reach the backend via a `/health` route. | Done | not |  | None | None | Unused
Implementation | P401 | Implement localStorage CRUD for questions | In the frontend `localStorageService`, implement `getQuestions`, `saveQuestion`, `updateQuestion`, and `deleteQuestion` functions with full TypeScript typing. | Done | yes | now, let's advance to the implementation phase. first, Implement localStorage CRUD for questions. In the frontend `localStorageService`, implement `getQuestions`, `saveQuestion`, `updateQuestion`, and `deleteQuestion` functions with full TypeScript typing. | Ask before edit | None | Excelent
Implementation | P401-1 | Implement initial UX | To Implement the inital UX, the home page layout, navbar and routes. | Done | yes | Prompt 1: Considering the project contexts and its goals, what's the best way to define the homepage layout and the site flow? Prompt 2: Let's begin implementing the first steps: Create the layout shell (AppLayout.tsx) with the top nav and a <Outlet /> Configure React Router in main.tsx with all routes above. Create all the initial page components and make the navbar functional so the user can navigate between the pages. Don't worry about to develop those page components at this moment. We'll do it in the next steps. Prompt 3: Let's make some changes in the dashboard (homepage) page and the navbar. Add a temporary router to render DesignPreview page Move the fixed navbar to the left side and the <page content> to the right. Check the navbar reference in the DS Ref/PageRef_01 - Home Page.png | Plan | None | Ok | Prompt 1: Perfectly gave me the insights. Prompt 2: Perfectly created Prompt 3: Good, but for DS and UX features, it needs to explain carefully to attempt the goals. Maybe using Figma data could improve the results.
Implementation | P402 | Implement question creation UI | Build the question creation page: a form with a statement field, dynamic list of alternatives (each with description and correct/incorrect toggle), and save to localStorage. | Done | yes | Prompt 1: We are implementing the question creation page. Before writing any code, confirm you have read and understood: 1. CLAUDE.md — especially sections 4 (localStorage), 6 (component conventions), and 7 (custom hooks) 2. src/types/index.ts — specifically the Question and Alternative interfaces 3. src/services/localStorageService.ts — specifically the saveQuestion function 4. src/components/index.ts — the available UI primitives List the relevant types and functions you will use before proceeding. Do not write any code yet. ------------------- Prompt 2: Create the file src/hooks/useQuestionForm.ts. This hook manages the local state for the question creation form. It must NOT contain any JSX. State it must manage: - statement: string (the question text) - alternatives: Alternative[] (dynamic list, minimum 2, maximum 6) Actions it must expose: - setStatement(value: string): void - addAlternative(): void -appends a new Alternative with an auto-generated id (use crypto.randomUUID()), empty description, and isCorrect: false - does nothing if alternatives.length >= 6 - removeAlternative(id: string): void -does nothing if alternatives.length <= 2 - updateAlternative(id: string, changes: Partial<Alternative>): void - toggleCorrect(id: string): void - flips the isCorrect value of the given alternative - reset(): void -resets form to initial state (empty statement, 2 blank alternatives) Validation it must expose: - isValid: boolean - true only when: statement is not empty AND at least one alternative has isCorrect: true AND all alternatives have non-empty descriptions It must import Alternative from src/types/index.ts. It must NOT call localStorageService — that happens in the page. Only create src/hooks/useQuestionForm.ts. | Plan | None | Excelent | Good but need to split the details
Implementation | P402-1 | Create UI aternative component | create the alternative component to be use in the question creation | Done | yes | Create the file src/components/UI/AlternativeItem.tsx. This component renders a single alternative row inside the question creation form. Props: - alternative: Alternative - index: number (used to display "Alternative A", "Alternative B"… using String.fromCharCode(65 + index)) - onUpdate: (id: string, changes: Partial<Alternative>) => void - onToggleCorrect: (id: string) => void - onRemove: (id: string) => void - canRemove: boolean (false when there are only 2 alternatives) It must render: - A letter label (A, B, C…) - A text input for the alternative description (use our Input component) - A toggle or checkbox to mark as correct (label: "Correct answer") — when isCorrect is true, highlight the row with a distinct background using our success color token - A remove button (use our Button component, variant danger, size sm) — disabled when canRemove is false Only create src/components/AlternativeItem.tsx. | Plan | None | Excelent | It met all the specified requirements.
| P402-2 | Create Question Creation Page | Implement the QuestionCreatePage.tsx page to allow users to create questions using form state management via useQuestionForm, persist data with saveQuestion, and handle navigation and validation. The page should include a structured form layout with alternatives management, validation feedback, and proper error handling without using alerts. | Done | yes | Create the file src/pages/questions/QuestionCreatePage.tsx. This is the question creation page. It must: Use the useQuestionForm hook for all form state Use the saveQuestion function from localStorageService for persistence Use useNavigate from React Router to redirect to /questions after a successful save Use the PageHeader, FormLayout, Textarea, Button, and AlternativeItem components Layout structure: PageHeader with title "New Question" and no action button FormLayout wrapping the entire form A Textarea for the statement: Label: "Question statement" Required Minimum 10 characters validation A section titled "Alternatives" with an "Add alternative" button: Variant: secondary Disabled when alternatives.length >= 6 A list of AlternativeItem components: One per alternative Pass handlers from useQuestionForm A helper text showing how many correct answers are selected: Example: "1 correct answer selected" Use danger color when zero A bottom action bar with: "Cancel" button: Variant: ghost Navigates to /questions "Save question" button: Variant: primary Type: submit Disabled when isValid is false Calls saveQuestion and navigates to /questions on success Error handling: Wrap saveQuestion in try/catch If an error occurs, display an error message: Use a Banner or inline text Use danger color Do NOT use alert() Only create src/pages/questions/QuestionCreatePage.tsx. | Ask before edit | None | Excelent | Safe to use
Implementation | P403 | Implement question listing UI | Build the questions list page showing all questions from localStorage, with edit and delete actions per row. | Done | yes | Prompt 1 (create hook): Create the file src/hooks/useQuestions.ts. This hook is responsible for managing the question list state. It must NOT contain any JSX. Responsibilities: State: - questions: Question[] - isLoading: boolean - error: string ¦ null Behavior: - On mount, load all questions using localStorageService - Wrap all calls in try/catch Actions: - refresh(): void → reloads questions from storage - deleteQuestion(id: string): void → removes the question using localStorageService → updates local state after deletion → must NOT mutate state directly Derived state: - isEmpty: boolean (questions.length === 0) Rules: - Import Question from src/types/index.ts - Use only localStorageService for data access - No direct localStorage usage - No JSX Only create src/hooks/useQuestions.ts. --------------------- Prompt 2 (render question cards): Update src/pages/questions/QuestionListPage.tsx. This page must: 1. Use the useQuestions hook 2. Use React Router (useNavigate) for navigation 3. Use PageHeader, Table, Button, and QuestionCard components Layout: - If isLoading: → show loading text (no spinner library) - If error: → show error message using text-agt-error - If isEmpty: → show empty state: "No questions created yet" - Otherwise: → render list of questions using the Question Card component: Display the question card in a gallery view. check the image in the DS Ref/PageRef_02 - Exam List.png Actions: - onEdit(id): → navigate to /questions/edit/:id (even if page not implemented yet) - onDelete(id): → confirm before deleting (use window.confirm) Rules: - No direct localStorage usage - No business logic outside the hook - Use only components from src/components/ tell me if you need more context | Auto edit
| P403-01 | Create question Card | Create the question card component to be used in question bank gallery | Done | yes | Now, let's render the question bank properly. Let's begin creating a Question Card component. Add a new folder to this component on the path System/Frontend/src/components This card should contain - Question title: displays the Question statement. if the text exceed two lines, add "..." - the correct Answer a divider in litter dots format ....................... - below the divider and left side, a short button to edit - below the divider and right side, a short a button do delete - check the layout reference in the file: DS Ref/PageRef_11 - Question card.png | Ask before edit | None | Ok | worked but not reached the styles ideas and references | styles need more context
Implementation | P404 | Implement question update UI | Build the question edit page, pre-populating the form from localStorage and saving updates back. | Done | yes | Prompt 1 (reinforcement): We are implementing the question edit page. Before writing any code, confirm you have read and understood: 1. CLAUDE.md — especially: - Section 4 (localStorage rules) - Section 6 (component conventions) - Section 7 (custom hooks) 2. src/types/index.ts — specifically: - Question - Alternative 3. src/services/localStorageService.ts — specifically: - getQuestions (or equivalent) - updateQuestion (or equivalent) - any helper used in saveQuestion 4. src/hooks/useQuestionForm.ts — this MUST be reused 5. src/pages/questions/QuestionCreatePage.tsx — this will be the base 6. src/components/UI/: - PageHeader - FormLayout - Textarea - Button - AlternativeItem List: - the Question type - how a question is retrieved by id - how a question is updated - how useQuestionForm currently works Do NOT write code yet. Prompt 2 (implementing): Create the file src/hooks/useQuestions.ts. This hook is responsible for managing the question list state. It must NOT contain any JSX. Responsibilities: State: - questions: Question[] - isLoading: boolean - error: string ¦ null Behavior: - On mount, load all questions using localStorageService - Wrap all calls in try/catch Actions: - refresh(): void → reloads questions from storage - deleteQuestion(id: string): void → removes the question using localStorageService → updates local state after deletion → must NOT mutate state directly Derived state: - isEmpty: boolean (questions.length === 0) Rules: - Import Question from src/types/index.ts - Use only localStorageService for data access - No direct localStorage usage - No JSX Only create src/hooks/useQuestions.ts. | Ask before edit | None | Excelent | Prompt 1: Safe to use Prompt 2: Good if split. But for layout features, needs more contexts
Implementation | P405 | Implement question deletion | Add a confirmation modal to the delete action on the question list. Remove the question from localStorage on confirm. | Done | yes |  | Ask before edit | None | Excelent |  | No prompt necessary. This feature was autocreated in the previous prompt
Implementation | P406 | Implement localStorage CRUD for exams | In `localStorageService`, implement `getExams`, `saveExam`, `updateExam`, and `deleteExam` functions. | Done | yes | We are implementing localStorage CRUD for exams. Before writing any code, confirm you have read and understood: 1. CLAUDE.md — especially: - Section 4 (localStorage rules) - Section 5 (TypeScript conventions) - Section 10 (code quality rules) 2. src/types/index.ts — specifically: - Exam interface - ExamIdentificationMode 3. src/services/localStorageService.ts — especially: - getQuestions - saveQuestion - updateQuestion - deleteQuestion - how STORAGE_KEYS is defined List: - the Exam type shape - the STORAGE_KEYS currently defined - how question CRUD functions are implemented (patterns to reuse) Do NOT write any code yet. Open src/services/localStorageService.ts. Update STORAGE_KEYS to include: EXAMS: 'agt:exams' Rules: - Do NOT change existing keys - Follow the exact naming pattern already used Only modify STORAGE_KEYS. In src/services/localStorageService.ts, implement or update: getExams(): Exam[] Behavior: - Read from STORAGE_KEYS.EXAMS - Parse JSON safely - If no data exists → return empty array - Wrap in try/catch - On error: → log error (console.error allowed inside service) → return empty array Rules: - Return type must be Exam[] - No any types - Follow same pattern as getQuestions Only implement getExams. In src/services/localStorageService.ts, implement or update: saveExam(exam: Omit<Exam, 'id' ¦ 'createdAt'>): Exam Behavior: - Retrieve existing exams - Create new exam: - id: crypto.randomUUID() - createdAt: new Date().toISOString() - Append new exam - Save back to localStorage - Return created exam Rules: - Do NOT mutate original array - Use JSON.stringify - Wrap in try/catch and throw error if save fails - Follow same pattern as saveQuestion Only implement saveExam. In src/services/localStorageService.ts, implement or update: updateExam(updatedExam: Exam): Exam Behavior: - Retrieve existing exams - Find exam by id - If not found → throw error ("Exam not found") - Replace the matching exam: - preserve id - preserve createdAt - Save updated array to localStorage - Return updated exam Rules: - Do NOT mutate array directly - Use map() to replace item - Wrap in try/catch and rethrow meaningful error - Follow same pattern as updateQuestion Only implement updateExam. In src/services/localStorageService.ts, implement: deleteExam(id: string): void Behavior: - Retrieve existing exams - Remove exam by id - Save updated array Rules: - Use filter() - Do NOT throw if exam does not exist (fail silently) - Wrap in try/catch and log error - Follow same pattern as deleteQuestion Only implement deleteExam. | Plan | None | Excelent | Merged 4 prompts in only one. It ensured the full and detailed context. Less token consumed
Implementation | P407 | Implement exam creation UI | Build the exam creation page: select questions from the registered list, choose identification mode (letters or powers of 2), and save to localStorage. | Done | yes | We are implementing the exam creation page. Start by creating a button Create Exam. Repeat the same pattern used in Question page. Build the exam creation page: select questions from the registered list, choose identification mode (letters or powers of 2), and save to localStorage. For more context, check the business documentation for this scope: "Test management (adding, changing, and removing). Each test is created from the selection of a set of questions previously registered in the system. The user must specify whether, for the test being created, the question alternatives should be identified by letters or by powers of 2 (1, 2, 4, 8, 16, 32, ...). In the case of letters, there must be a space after the question for the student to indicate the letters marked. In the case of powers, there must be a space for the student to indicate the sum of the alternatives marked by the student." | Plan | None | Excelent | He managed to create the entire structure without needing many instructions. This precision was due to the context acquired so far, or it could have been precisely achieved from the beginning? | From this row to the end, I'll start using more concise instructions. Overall impressions: Good prompt infomration -> less context used.
Implementation | P408 | Implement exam listing UI | Build the exams list page showing all exams from localStorage with edit and delete actions. | Done | yes | We are implementing the exam listing page. Start creating the Exam card: the exam card should use the same pattern layout used in question card, except for its height, which should be bigger than the question card. the exam card should display: the title exam, the description (if it exists) with limited characters (add ... if overlay), identification mode, amount of questions, Created date (formatted) the card should display the edit (onEdit) and delete (onDelete) button Create src/hooks/useExams.ts. This hook manages exam list state. Populate the exam list page (System/Frontend/src/pages/exams/ExamListPage.ts) with the same pattern used in the question page. | Plan | None | Excelent | He managed to create the entire structure without needing many instructions. This precision was due to the context acquired so far, or it could have been precisely achieved from the beginning.
Implementation | P409 | Implement exam update UI | Build the exam edit page, pre-populating selected questions and identification mode from localStorage and saving updates. | Done | yes | We are implementing the exam edit page. Goal: allow initialization with existing exam data. Update src/hooks/useExamForm.ts. Build the exam edit page, pre-populating selected questions and identification mode from localStorage and saving updates. Create edit page. Create src/pages/exams/ExamEditPage.tsx. Update navigation Open src/pages/exams/ExamListPage.tsx., Update onEdit(id). Update the router to /exams/edit/:id ExamEditPage. Ensure no existing routes are broken. | Plan | None | Excelent | The application doesn't break when a question registered in the exame is deleted. It automatically removes it.
Implementation | P410 | Implement exam deletion | Add a confirmation modal to the delete action on the exam list. Remove the exam from localStorage on confirm. | Done | yes |  | Ask before edit | none |  |  | Auto created in the previous prompt
Implementation | P411 | Implement PDF generation request | Build the frontend form to trigger PDF generation: select an exam, input the number of copies (N), and POST the exam data + N to the backend `/generate-pdf` endpoint. Download the returned file. | Done | yes | We are implementing the PDF generation feature. Let's begin by reviewing some project information: 1. CLAUDE.md — especially: - Section 4 (localStorage rules) - Section 8 (API communication) - Section 10 (code quality rules) 2. src/types/index.ts — specifically: - Exam - Question 3. src/services/localStorageService.ts: - getExams - getQuestions 4. src/services/apiService.ts: - how Axios instance is configured 5. Backend contract (from README): - POST /generate-pdf - receives exam data + N - returns a file (ZIP with PDFs + CSV) 6. Existing UI patterns: - QuestionListPage - ExamListPage - FormLayout, PageHeader, Input, Button Build the frontend form to trigger PDF generation: select an exam, input the number of copies (N), and POST the exam data + N to the backend `/generate-pdf` endpoint. Download the returned file. For more context, check the business rule: Generation of PDFs of a number (provided by the user) of individual tests, varying the order in which the questions and alternatives appear in each test. Each PDF must have the title of the test (with the name of the subject, professor, data, etc.). Each page of the test must have the number of the individual test generated by the system as a footer. There is no final PDF, but there must be space for the student to enter their name and CPF (Brazilian tax identification number). The system must also generate a CSV file with the answer key for each test. Each line of the CSV contains information about a test: the test number, followed by the answer key for each question of the test (the letters that should be selected, or the expected sum). This implementation consists only in the frontend. We'll dive deep in the backend later, but be read when we start. Tell me you need more context. | Plan | None | Excelent | GOod to retrieve the context | at this moment, Claude lost the context section and it was necessary ensure the persistence instructions
Implementation | P412 | Implement backend PDF generation | Build the Express route and pdfkit service to receive exam data and N, generate N randomized PDFs (randomized question and alternative order per copy), each with: header (course, instructor, date), footer with exam number, and a student name/CPF space at the end. Return as a downloadable ZIP or merged PDF. | Done | yes | We are implementing PDF generation in the backend. Before writing any code, confirm you have read and understood: 1. CLAUDE.md (backend) — especially: - Stateless architecture rules - Section 7 (PDF generation) - Section 12 (controllers vs services) 2. src/types/index.ts — specifically: - Exam - Question - Alternative - GeneratedExam 3. Existing structure: - src/controllers/ - src/routes/ - src/services/ - src/utils/shuffle.ts 4. API contract: - POST /generate-pdf - Receives: { exam: { id, title, identificationMode, questions: Question[] }, copies: number } 5. Constraints: - No database - No global state - No file persistence - Use pdfkit ONLY Build the Express route and pdfkit service to receive exam data and N, generate N randomized PDFs (randomized question and alternative order per copy), each with: header (course, instructor, date), footer with exam number, and a student name/CPF space at the end. Return as a downloadable ZIP or merged PDF. Check the business rule for the full context | Auto edit | The PDF file was bad formatted | Bad | Layout implementaton always requires accurace in the context
Implementation | P413 | Implement answer key CSV generation | As part of the PDF generation service, generate a CSV where each row contains the exam number followed by the expected answer per question (letters or power-of-2 sum). Return the CSV alongside the PDF. | Done | yes |  | Auto edit |  | Excelent |  | auto implemented in the previous prompt
Implementation | P414 | Implement grading upload UI | Build the frontend grading page: upload the answer key CSV and student responses CSV, select grading mode (Strict or Lenient), and POST all to the backend `/grade` endpoint. | InProgress | yes | Implement grading upload UI Build the frontend grading page: upload the answer key CSV and student responses CSV, select grading mode (Strict or Lenient), and POST all to the backend `/grade` endpoint. Consider the business rule for this thaks: Finally, the system must allow for the correction of tests and the generation of the class grade report. To correct the test, the system must be informed of the CSV file with the answer key and another CSV file with the answers provided by the student (usually through a Google Forms that collects the test number and the answer given by the student for each question). The test must be corrected in a more rigorous way (an incorrectly selected alternative or one left unselected will result in zero for the entire question) or less rigorous way (the question grade is proportional to the percentage of alternatives selected or left over from being incorrectly selected). | Auto edit |  | Excelent | Good, but high token consume | Add a feature to save the historic
Implementation | P415 | Implement backend strict grading | Build the Express route and grading service: implement strict mode where any incorrect or missing alternative selection invalidates the entire question. | InProgress | yes | Implement backend strict grading - Build the Express route and grading service: implement strict mode where any incorrect or missing alternative selection invalidates the entire question. - Check the business rule for more context: Finally, the system must allow for the correction of tests and the generation of the class grade report. To correct the test, the system must be provided with a CSV containing the answer key and another CSV containing the answers provided by the student (usually through a Google Forms that collects the test number and the answer given by the student for each question). The test must be corrected in a more rigorous way (an incorrectly selected or left unselected alternative results in a zero score for the entire question) or less rigorous way (the question's grade is proportional to the percentage of incorrectly selected or left unselected alternatives). | Auto edit | High token consume | Ok | It achieved its objective but has a high token usage. (from 52% to 67% section limit). | The less context offered in the prompt, the greater the use of tokens.
Implementation | P416 | Implement backend lenient grading | Extend the grading service: implement lenient mode where each question's score is proportional to the percentage of correctly selected or unselected alternatives. | Done | yes | Implement backend lenient grading Extend the grading service: implement lenient mode where each question's score is proportional to the percentage of correctly selected or unselected alternatives. | Auto edit | None | Excelent
Implementation | P417 | Implement grade report display | Build the frontend grade report page to display the grading results returned by the backend: per-student score per question and total grade for the class. | Done | yes |  | Auto edit | None | Excelent |  | No prompt necessary. This feature was auto created in the previous prompt
Implementation | P418 | Enforce TypeScript strict typing | Review all components, hooks, services, controllers, and utilities. Eliminate all implicit `any`. Enable `strict: true` in both `tsconfig.json` files. | Canceled | not |  | None |  | Unused
Implementation | P419 | Enforce modularity and clean code | Refactor repeated logic into custom React hooks (`useQuestions`, `useExams`) on the frontend and dedicated service modules on the backend. Ensure single responsibility per file. | Canceled | not |  | None |  | Unused
Implementation | P420 | Create admin page | This page will manage admin features and provide data to improve de testing performance | Done | yes | now, let's create some feature to improve our test phase. - first, create a new tab and route in the menu called "Admin". This new page will be responsible for managing the tests feature we'll create in the next tasks. | Auto edit | None | Excelent | Safe to use | Created propely
Implementation | P421 | Create Import question feature | Import questions through a CSV dataset to improve the tesintg d | Done | yes | In the admin page, add a feature to import questions through a CSV file. - This CSV could have multiples questions and its anserws - you have to choice the csv format according to the project structure - As well as the function of creating a question, the questions imported should be displayed on the question page as well as be able to add in an exam. by the end of this implementation, give me the instruction about how to import questions. | Auto edit | None | Excelent | Safe to use | Created propely
Implementation | P422 | Generate CSV questions | Create and CSV to be imported in this feature | Done | not |  | None |  | Unused
Testing | P501 | Install Cucumber and Gherkin | Install `@cucumber/cucumber` in both projects. Configure the test runner and set up the `features/` folder structure. | Done | yes | now, let's advance to testing phase. Install Cucumber and Gherkin Install @cucumber/cucumber in both projects. Configure the test runner and set up the features/ folder structure. | Auto edit | None | Excelent | installed correctly. safe to use
Testing | P502 | Write Gherkin scenarios – Questions | Write `.feature` files covering: creating a question with valid data, creating with missing statement, creating with no correct alternative, editing a question, and deleting a question. | Done | yes | Write Gherkin scenarios – Questions Write `.feature` files covering: creating a question with valid data, creating with missing statement, creating with no correct alternative, editing a question, and deleting a question. | Auto edit | None | Excelent | All test was passed. safe to use
Testing | P503 | Implement step definitions – Questions | Implement Cucumber step definitions that interact with the localStorage service (frontend) or simulate the data layer to validate question CRUD behavior. | Done | yes | Implement step definitions – Questions Implement Cucumber step definitions that interact with the localStorage service (frontend) or simulate the data layer to validate question CRUD behavior. | Auto edit | None | Excelent | All test was passed. safe to use | Found some errors and autofixed them.
Testing | P504 | Write Gherkin scenarios – Exams | Write `.feature` files covering: creating an exam with letter mode, creating with power-of-2 mode, editing an exam, deleting an exam, and creating an exam with no questions selected. | Done | yes | Write Gherkin scenarios – Exams Write `.feature` files covering: creating an exam with letter mode, creating with power-of-2 mode, editing an exam, deleting an exam, and creating an exam with no questions selected. | Auto edit | None | Excelent | All test was passed. safe to use
Testing | P505 | Implement step definitions – Exams | Implement step definitions for all exam-related Gherkin scenarios. | Done | yes | Implement step definitions for all exam-related Gherkin scenarios. | Auto edit | None | Excelent | All test was passed. safe to use | Found some errors and autofixed them.
Testing | P506 | Write Gherkin scenarios – PDF/CSV generation | Write `.feature` files covering: generating N PDFs with correct structure (header, footer, name/CPF space), randomized order across copies, and a valid CSV answer key output. | Done | yes | Write Gherkin scenarios – PDF/CSV generation Write `.feature` files covering: generating N PDFs with correct structure (header, footer, name/CPF space), randomized order across copies, and a valid CSV answer key output. | Auto edit | None | Excelent | All test was passed. safe to use
Testing | P507 | Implement step definitions – PDF/CSV | Implement step definitions that call the backend `/generate-pdf` endpoint and assert response structure and CSV content. | Done | yes | Implement step definitions – PDF/CSV Implement step definitions that call the backend `/generate-pdf` endpoint and assert response structure and CSV content. | Auto edit | None | Excelent | All test was passed. safe to use | Found some errors and autofixed them.
Testing | P508 | Write Gherkin scenarios – Grading | Write `.feature` files covering: strict grading with all correct answers, strict grading with one wrong answer, lenient grading with partial answers, and invalid CSV upload handling. | Done | yes | Write Gherkin scenarios – Grading Write `.feature` files covering: strict grading with all correct answers, strict grading with one wrong answer, lenient grading with partial answers, and invalid CSV upload handling. | Auto edit | None | Excelent | All test was passed. safe to use
Testing | P509 | Implement step definitions – Grading | Implement step definitions that POST to the backend `/grade` endpoint and assert grading results and report structure. | Done | yes | Implement step definitions – Grading Implement step definitions that POST to the backend `/grade` endpoint and assert grading results and report structure. | Auto edit |  | Excelent
Testing | P510 | Run full test suite and collect evidence | Execute all tests. Capture output logs and screenshots as required evidence. Fix any failures and re-run until all pass. | Done | not |  | None |  | Unused | All test was passed
Documentation | P607 | Create Testing Document | Create a doc with the instructions about how to test using cucumbre | Done | yes | We are done with the testing phase. Let's advance with the documentation phase. - Begin creating the "How to test" markdown file in the Docs folder. - Write a short instruction about how to create test scenarios and how to run them. | Auto edit |  | Excelent
Documentation | P601 | Write user README (frontend) | Update the frontend README with: how to access the system, how to use each feature (questions, exams, PDF generation, grading), and a note that data is stored in the browser's localStorage. | Done | yes | Write user README (frontend) - Update the frontend README to guarantee it contains: how to access the system, how to use each feature (questions, exams, PDF generation, grading), and a note that data is stored in the browser's localStorage. - Update the project structure map | Auto edit |  | Unused
Documentation | P602 | Write developer README (backend) | Update the backend README with: setup instructions, all API endpoint references (routes, request/response format), environment variable reference, and how to run tests. | Done | yes | Write developer README (backend) - Update the backend README with: setup instructions, all API endpoint references (routes, request/response format), environment variable reference, and how to run tests. - Update the project structure map | Auto edit |  | Unused
Documentation | P603 | Create system flowchart | Create a flowchart (Mermaid or draw.io) covering the full user journey: create questions → create exam → generate PDFs + answer key CSV → collect responses → upload and grade → view report. | Pending | not |  | None |  | Unused
Documentation | P604 | Document API endpoints | Write or generate (Swagger/OpenAPI) a full API reference for all backend routes: `/generate-pdf`, `/grade`, and `/health`, including request body schemas and response formats. | Pending | not |  | None |  | Unused
Documentation | P605 | Document TypeScript interfaces | Write a developer reference document describing all key TypeScript types and interfaces, their fields, and their usage context. | Pending | not |  | None |  | Unused
Documentation | P606 | Document CSV data formats | Document the expected format of the student responses CSV (Google Forms format) and the answer key CSV, with field descriptions and example rows. | Pending | not |  | None |  | Unused
Deployment | P701 | Configure production env variables | Create production environment variables for both projects. Frontend: `VITE_API_BASE_URL` pointing to the Railway backend URL. Backend: `PORT`. | Done | not |  | None |  | Unused
Deployment | P702 | Build frontend for production | Run `npm run build` and verify the output bundle. Test locally with a static server (`npx serve dist`) before deploying. | Done | not |  | None |  | Unused
Deployment | P703 | Deploy frontend to Vercel | Connect the frontend GitHub repo to Vercel. Configure build command, output directory, and environment variables. Deploy and verify the live URL. | Done | not |  | None |  | Unused
Deployment | P704 | Deploy backend to Railway | Connect the backend GitHub repo to Railway. Configure the start command (`node dist/index.js`), build command (`tsc`), PORT, and environment variables. Deploy and verify the live URL. | Done | not |  | None |  | Unused
Deployment | P705 | Update and verify cross-origin config | Ensure the backend CORS configuration allows requests from the Vercel frontend production URL. Test end-to-end on the live URLs. | Canceled | not |  | None |  | Unused
Deployment | P706 | Smoke test production deployment | Manually test all major features on the live URLs: question CRUD, exam CRUD, PDF generation with download, CSV download, and grading flow. | Done | not |  | None |  | Unused
Deployment | P707 | (Optional) Configure CI pipeline | Set up GitHub Actions to run the test suite automatically on every push to `main` or `develop`. | Done | not |  | None |  | Unused
Deployment | P708 | (Optional) Configure CD pipeline | Set up GitHub Actions to automatically deploy to Vercel and Railway on successful merge to `main`. | Done | not |  | None |  | Unused
Partner Review | P801 | Access assigned colleague's repo | Receive and access the GitHub repository link from your assigned colleague for review. |  |  |  | None |  | Unused
Partner Review | P802 | Evaluate system functionality | Verify whether the colleague's system implements all four required features: question management, exam management, PDF generation, and grading (strict and lenient modes). |  |  |  | None |  | Unused
Partner Review | P803 | Evaluate code and test quality | Assess code quality (modularity, TypeScript types, clean code) and test quality (Gherkin coverage, step definitions, edge cases). |  |  |  | None |  | Unused
Partner Review | P804 | Compare systems | Compare the colleague's system to yours in terms of functionality completeness, architectural decisions, and overall quality. |  |  |  | None |  | Unused
Partner Review | P805 | Review development history | Read the colleague's `HistóricoDoMeuExperimento.xlsx`. Summarize their agent interaction strategies, situations where the agent excelled or failed, and types of problems observed. |  |  |  | None |  | Unused
Partner Review | P806 | Write RevisãoDoSistemaDoMeuColega.md | Write the complete review document answering: functionality evaluation, code/test quality issues, comparison with your system, development history summary, and overall agent usefulness evaluation. |  |  |  | None |  | Unused
Partner Review | P807 | Submit repository link | Submit your GitHub repository link in the activity platform and send it directly to your assigned reviewer. |  |  |  | None |  | Unused
Bug Fix | P908 | Fix exam card layout | Fix the and the organize the exam card buttons | Done | yes | Let's improve the exam card layout. in the small screens, the buttons overlay the card. Make the card flex. Reorder the buttons according to the following sequence: Generate PDF (primary), Grade (Secondary), Edit (ghost), Delete (danger) | Auto edit | None | Excelent | Bug perfectly fixed | caused by the addition of unplanned buttons
Extra feature | P908 | Improve menu navbar |  | Done | yes | let's make some layout changes. in the menu, add a divider below exams tab. make the admin and design preview options ghost style | None | None | Excelent | Safe for small layout tasks
Extra feature | P909 | Add mobile and tablet menu |  | Done | yes | Let's improve some responsiveness for small and medium sizes. Add an open/close menu in the small sizes. | None |  | Unused
Extra feature | P910 | Improve DS page responsiveness |  | Done | yes | now, improve responsiveness for small and medium sizes for the design preview page | None |  | Unused
Extra feature | P911 | Add search bar in the question and exam page |  | Done | yes | adding search bar. in the questions page, implement the search bar to search for question by the question title> In the exam question, implement the search bar to search for exam by the exam title | None |  | Unused
Extra feature | P912 | Add search bar in the exam form |  | Done | yes | Add search bar in the exam creating form. | None |  | Unused
Extra feature | P913

## Página2 (hidden)
01. Initial Configuration
Phase | Code | Title | Description
Initial Config | P1-01 | Install Node.js and npm | Install Node.js (LTS) and npm on your local machine. Verify with `node -v` and `npm -v`.
Initial Config | P1-02 | Install Git | Install Git and configure global user name and email.
Initial Config | P1-03 | Create GitHub repositories | Create two GitHub repositories under a parent `sistema/` folder: `sistema-frontend` and `sistema-backend`, as required by the final repo spec.
Initial Config | P1-04 | Initialize frontend project | Scaffold a React + TypeScript project using Vite (`npm create vite@latest`). Select the React + TypeScript template.
Initial Config | P1-05 | Install and configure Tailwind CSS | Install Tailwind CSS and its dependencies. Configure `tailwind.config.js` and add Tailwind directives to the global CSS file.
Initial Config | P1-06 | Initialize backend project | Create a Node.js + TypeScript project for the backend. Run `npm init`, install TypeScript, and configure `tsconfig.json`.
Initial Config | P1-07 | Install Express and types | Install Express and `@types/express` in the backend project.
Initial Config | P1-08 | Configure ESLint and Prettier | Install and configure ESLint and Prettier for both frontend and backend to enforce consistent code style.
Initial Config | P1-09 | Set up .gitignore files | Create proper `.gitignore` files for both projects (ignoring `node_modules`, `.env`, `dist`, etc.).
Initial Config | P1-10 | Create Excel experiment log | Create `HistóricoDoMeuExperimento.xlsx` in the repository root to log the experiment history as required.
Initial Config | P1-11 | Create partner review placeholder | Create `RevisãoDoSistemaDoMeuColega.md` in the repository root (to be filled in Phase 8).
Initial Config | P1-12 | Push initial code to GitHub | Commit and push the initial scaffolding for both frontend and backend to their respective GitHub repositories.
02. Agent Configuration
Phase | Code | Title | Description
Agent Config | P2-01 | Install VS Code | Install Visual Studio Code on your local machine if not already installed.
Agent Config | P2-02 | Install Claude Code extension | Install the Claude Code agent in VS Code following Anthropic's official setup instructions.
Agent Config | P2-03 | Authenticate Claude Code | Log in and authenticate the Claude Code extension with your Anthropic account.
Agent Config | P2-04 | Create CLAUDE.md for frontend | Create a `CLAUDE.md` file in the frontend repo with persistent instructions: stack (React, TypeScript, Tailwind), localStorage as the data layer, coding conventions, folder structure, and system domain context.
Agent Config | P2-05 | Create CLAUDE.md for backend | Create a `CLAUDE.md` file in the backend repo with persistent instructions: Express + TypeScript, stateless architecture (no database), pdfkit for PDF generation, grading and CSV logic only, and API design conventions.
Agent Config | P2-06 | Define agent skills and tools | Document which Claude Code built-in tools will be used (file editing, terminal, search). Configure or enable them as needed in the project.
Agent Config | P2-07 | Validate agent setup | Run a simple test prompt in Claude Code (e.g., "create a Hello World Express route") to confirm the agent is working inside both projects.
03. Architecture and Design System Definition
Phase | Code | Title | Description
Architecture | P3-01 | Define frontend folder structure | Create the frontend folder structure: `components/`, `pages/`, `hooks/`, `services/`, `types/`, `utils/`, `assets/`.
Architecture | P3-02 | Define backend folder structure | Create the backend folder structure: `controllers/`, `routes/`, `services/`, `utils/`, `types/`, `middlewares/`.
Architecture | P3-03 | Install frontend libraries | Install: React Router (navigation), Axios (HTTP client to call backend), and `papaparse` (CSV parsing on the frontend for student response uploads).
Architecture | P3-04 | Install backend libraries | Install: `cors`, `dotenv`, `pdfkit` + `@types/pdfkit` (PDF generation), `csv-parse` (parsing uploaded CSVs), and `multer` (handling CSV file uploads from the frontend).
Architecture | P3-05 | Define TypeScript types | Create shared TypeScript interfaces: `Question`, `Alternative`, `Exam`, `ExamIdentificationMode` (letter | power-of-two), `GeneratedExam`, `AnswerKey`, `StudentResponse`, `GradingResult`, `GradeReport`.
Architecture | P3-06 | Create localStorage service | Build a typed `localStorageService.ts` utility in the frontend that handles all read/write operations for questions and exams, with JSON serialization and error handling.
Architecture | P3-07 | Define Tailwind design tokens | Research design references from similar apps (e.g., Google Forms). Define color palette, typography scale, spacing, and button/input styles as Tailwind theme extensions in `tailwind.config.js`.
Architecture | P3-08 | Create base UI components | Scaffold reusable components: `Button`, `Input`, `Textarea`, `Modal`, `Table`, `Card`, `Badge`, `FormLayout`, and `PageHeader`.
Architecture | P3-09 | Configure environment variables | Create `.env` and `.env.example` for both projects. Frontend: `VITE_API_BASE_URL`. Backend: `PORT`.
Architecture | P3-10 | Define Git flow and commit conventions | Document branching strategy (`main`, `develop`, `feature/P{n}-{code}-{slug}`), commit message format (Conventional Commits), and push rules. Add to README.
Architecture | P3-11 | Write initial README.md files | Write initial README.md for both repos: project description, stack, how to run locally, folder structure, and environment variable reference.
Architecture | P3-12 | Run projects locally | Start both the frontend dev server and the backend (nodemon + ts-node). Verify the frontend can reach the backend via a `/health` route.
04. Project Implementation
Phase | Code | Title | Description
Implementation | P4-01 | Implement localStorage CRUD for questions | In the frontend `localStorageService`, implement `getQuestions`, `saveQuestion`, `updateQuestion`, and `deleteQuestion` functions with full TypeScript typing.
Implementation | P4-02 | Implement question creation UI | Build the question creation page: a form with a statement field, dynamic list of alternatives (each with description and correct/incorrect toggle), and save to localStorage.
Implementation | P4-03 | Implement question listing UI | Build the questions list page showing all questions from localStorage, with edit and delete actions per row.
Implementation | P4-04 | Implement question update UI | Build the question edit page, pre-populating the form from localStorage and saving updates back.
Implementation | P4-05 | Implement question deletion | Add a confirmation modal to the delete action on the question list. Remove the question from localStorage on confirm.
Implementation | P4-06 | Implement localStorage CRUD for exams | In `localStorageService`, implement `getExams`, `saveExam`, `updateExam`, and `deleteExam` functions.
Implementation | P4-07 | Implement exam creation UI | Build the exam creation page: select questions from the registered list, choose identification mode (letters or powers of 2), and save to localStorage.
Implementation | P4-08 | Implement exam listing UI | Build the exams list page showing all exams from localStorage with edit and delete actions.
Implementation | P4-09 | Implement exam update UI | Build the exam edit page, pre-populating selected questions and identification mode from localStorage and saving updates.
Implementation | P4-10 | Implement exam deletion | Add a confirmation modal to the delete action on the exam list. Remove the exam from localStorage on confirm.
Implementation | P4-11 | Implement PDF generation request | Build the frontend form to trigger PDF generation: select an exam, input the number of copies (N), and POST the exam data + N to the backend `/generate-pdf` endpoint. Download the returned file.
Implementation | P4-12 | Implement backend PDF generation | Build the Express route and pdfkit service to receive exam data and N, generate N randomized PDFs (randomized question and alternative order per copy), each with: header (course, instructor, date), footer with exam number, and a student name/CPF space at the end. Return as a downloadable ZIP or merged PDF.
Implementation | P4-13 | Implement answer key CSV generation | As part of the PDF generation service, generate a CSV where each row contains the exam number followed by the expected answer per question (letters or power-of-2 sum). Return the CSV alongside the PDF.
Implementation | P4-14 | Implement grading upload UI | Build the frontend grading page: upload the answer key CSV and student responses CSV, select grading mode (Strict or Lenient), and POST all to the backend `/grade` endpoint.
Implementation | P4-15 | Implement backend strict grading | Build the Express route and grading service: implement strict mode where any incorrect or missing alternative selection invalidates the entire question.
Implementation | P4-16 | Implement backend lenient grading | Extend the grading service: implement lenient mode where each question's score is proportional to the percentage of correctly selected or unselected alternatives.
Implementation | P4-17 | Implement grade report display | Build the frontend grade report page to display the grading results returned by the backend: per-student score per question and total grade for the class.
Implementation | P4-18 | Enforce TypeScript strict typing | Review all components, hooks, services, controllers, and utilities. Eliminate all implicit `any`. Enable `strict: true` in both `tsconfig.json` files.
Implementation | P4-19 | Enforce modularity and clean code | Refactor repeated logic into custom React hooks (`useQuestions`, `useExams`) on the frontend and dedicated service modules on the backend. Ensure single responsibility per file.
05. Testing
Phase | Code | Title | Description
Testing | P5-01 | Install Cucumber and Gherkin | Install `@cucumber/cucumber` in both projects. Configure the test runner and set up the `features/` folder structure.
Testing | P5-02 | Write Gherkin scenarios – Questions | Write `.feature` files covering: creating a question with valid data, creating with missing statement, creating with no correct alternative, editing a question, and deleting a question.
Testing | P5-03 | Implement step definitions – Questions | Implement Cucumber step definitions that interact with the localStorage service (frontend) or simulate the data layer to validate question CRUD behavior.
Testing | P5-04 | Write Gherkin scenarios – Exams | Write `.feature` files covering: creating an exam with letter mode, creating with power-of-2 mode, editing an exam, deleting an exam, and creating an exam with no questions selected.
Testing | P5-05 | Implement step definitions – Exams | Implement step definitions for all exam-related Gherkin scenarios.
Testing | P5-06 | Write Gherkin scenarios – PDF/CSV generation | Write `.feature` files covering: generating N PDFs with correct structure (header, footer, name/CPF space), randomized order across copies, and a valid CSV answer key output.
Testing | P5-07 | Implement step definitions – PDF/CSV | Implement step definitions that call the backend `/generate-pdf` endpoint and assert response structure and CSV content.
Testing | P5-08 | Write Gherkin scenarios – Grading | Write `.feature` files covering: strict grading with all correct answers, strict grading with one wrong answer, lenient grading with partial answers, and invalid CSV upload handling.
Testing | P5-09 | Implement step definitions – Grading | Implement step definitions that POST to the backend `/grade` endpoint and assert grading results and report structure.
Testing | P5-10 | Run full test suite and collect evidence | Execute all tests. Capture output logs and screenshots as required evidence. Fix any failures and re-run until all pass.
06. Documentation
Phase | Code | Title | Description
Documentation | P6-01 | Write user README (frontend) | Update the frontend README with: how to access the system, how to use each feature (questions, exams, PDF generation, grading), and a note that data is stored in the browser's localStorage.
Documentation | P6-02 | Write developer README (backend) | Update the backend README with: setup instructions, all API endpoint references (routes, request/response format), environment variable reference, and how to run tests.
Documentation | P6-03 | Create system flowchart | Create a flowchart (Mermaid or draw.io) covering the full user journey: create questions → create exam → generate PDFs + answer key CSV → collect responses → upload and grade → view report.
Documentation | P6-04 | Document API endpoints | Write or generate (Swagger/OpenAPI) a full API reference for all backend routes: `/generate-pdf`, `/grade`, and `/health`, including request body schemas and response formats.
Documentation | P6-05 | Document TypeScript interfaces | Write a developer reference document describing all key TypeScript types and interfaces, their fields, and their usage context.
Documentation | P6-06 | Document CSV data formats | Document the expected format of the student responses CSV (Google Forms format) and the answer key CSV, with field descriptions and example rows.
07. Deployment
Phase | Code | Title | Description
Deployment | P7-01 | Configure production env variables | Create production environment variables for both projects. Frontend: `VITE_API_BASE_URL` pointing to the Railway backend URL. Backend: `PORT`.
Deployment | P7-02 | Build frontend for production | Run `npm run build` and verify the output bundle. Test locally with a static server (`npx serve dist`) before deploying.
Deployment | P7-03 | Deploy frontend to Vercel | Connect the frontend GitHub repo to Vercel. Configure build command, output directory, and environment variables. Deploy and verify the live URL.
Deployment | P7-04 | Deploy backend to Railway | Connect the backend GitHub repo to Railway. Configure the start command (`node dist/index.js`), build command (`tsc`), PORT, and environment variables. Deploy and verify the live URL.
Deployment | P7-05 | Update and verify cross-origin config | Ensure the backend CORS configuration allows requests from the Vercel frontend production URL. Test end-to-end on the live URLs.
Deployment | P7-06 | Smoke test production deployment | Manually test all major features on the live URLs: question CRUD, exam CRUD, PDF generation with download, CSV download, and grading flow.
Deployment | P7-07 | (Optional) Configure CI pipeline | Set up GitHub Actions to run the test suite automatically on every push to `main` or `develop`.
Deployment | P7-08 | (Optional) Configure CD pipeline | Set up GitHub Actions to automatically deploy to Vercel and Railway on successful merge to `main`.
08. Partner Review
Phase | Code | Title | Description
Partner Review | P8-01 | Access assigned colleague's repo | Receive and access the GitHub repository link from your assigned colleague for review.
Partner Review | P8-02 | Evaluate system functionality | Verify whether the colleague's system implements all four required features: question management, exam management, PDF generation, and grading (strict and lenient modes).
Partner Review | P8-03 | Evaluate code and test quality | Assess code quality (modularity, TypeScript types, clean code) and test quality (Gherkin coverage, step definitions, edge cases).
Partner Review | P8-04 | Compare systems | Compare the colleague's system to yours in terms of functionality completeness, architectural decisions, and overall quality.
Partner Review | P8-05 | Review development history | Read the colleague's `HistóricoDoMeuExperimento.xlsx`. Summarize their agent interaction strategies, situations where the agent excelled or failed, and types of problems observed.
Partner Review | P8-06 | Write RevisãoDoSistemaDoMeuColega.md | Write the complete review document answering: functionality evaluation, code/test quality issues, comparison with your system, development history summary, and overall agent usefulness evaluation.
Partner Review | P8-07 | Submit repository link | Submit your GitHub repository link in the activity platform and send it directly to your assigned reviewer.